## Projects
Project ID | Project Name | Description | Department | Strategic Pillar | Program | Parent Project ID | Project Manager | Executive Sponsor | Vendor | Status | Health | Priority | Phase | Approval Date | Start Date | Target End Date | Actual End Date | Budget | Spent | Currency | Percent Complete | Last Updated
PRJ-1001 | OneCare EMR Modernization Program | Enterprise umbrella for replacing legacy EMRs with a single clinical record across all facilities. | Digital Health | Digital Transformation | OneCare EMR |  | Fatima Al Zaabi | Catherine Dubois | Epic Systems | In Progress | Amber | Critical | Execution | 2024-01-18 | 2024-03-04 | 2027-03-31 |  | 45000000 | 26191000 | AED | 68 | 2026-08-21
PRJ-1002 | EMR Core Build & Clinical Configuration | Core EMR module build, clinical content localization and specialty workflow configuration. | Digital Health | Digital Transformation | OneCare EMR | PRJ-1001 | Ravi Subramanian | Dr. Richard Hughes | Epic Systems | In Progress | Green | Critical | Execution | 2025-02-09 | 2025-02-24 | 2026-10-11 |  | 19300000 | 12019000 | AED | 74 | 2026-08-13
PRJ-1003 | Legacy Data Migration Factory | Extraction, cleansing and conversion of 14 years of patient records from three legacy systems. | Digital Health | Digital Transformation | OneCare EMR | PRJ-1001 | Khalid Al Marzooqi | Amna Al Ali | Accenture | In Progress | Red | Critical | Execution | 2025-02-01 | 2025-03-15 | 2026-06-30 |  | 9100000 | 10119000 | AED | 62 | 2026-08-20
PRJ-1004 | Clinical Order Sets & CPOE Rollout | Standardized evidence-based order sets and computerized provider order entry across inpatient units. | Digital Health | Patient-Centric Care | OneCare EMR | PRJ-1001 | Mariam Al Suwaidi | Mohammed Al Hashimi | Epic Systems | Completed | Green | Medium | Closure | 2025-05-12 | 2025-07-29 | 2026-08-14 | 2026-08-19 | 7450000 | 6716000 | AED | 100 | 2026-08-20
PRJ-1005 | e-Prescribing & Pharmacy Integration | Closed-loop medication management integrating e-prescribing with pharmacy dispensing systems. | Digital Health | Patient-Centric Care | OneCare EMR | PRJ-1001 | Daniel Weber | Eng. Salem Al Nuaimi | Epic Systems | In Progress | Amber | High | Monitoring | 2025-04-16 | 2025-06-09 | 2026-11-02 |  | 6350000 | 4391000 | AED | 77 | 2026-07-19
PRJ-1006 | Go-Live Command Center & Training | At-the-elbow support model, super-user network and 24x7 command center for EMR go-live waves. | Digital Health | Operational Excellence | OneCare EMR | PRJ-1001 | Omar Al Shamsi | Catherine Dubois | Accenture | Approved | Green | Low | Planning | 2026-07-10 | 2026-10-01 | 2027-10-14 |  | 3250000 | 75000 | AED | 7 | 2026-08-02
PRJ-1010 | Fortress Cyber Resilience Program | Umbrella program uplifting cyber defense, detection and response to national regulatory standards. | Cybersecurity | Resilience & Security | Fortress |  | Khalid Al Marzooqi | Amna Al Ali | CrowdStrike | In Progress | Green | Critical | Execution | 2024-07-10 | 2024-09-02 | 2026-12-31 |  | 30000000 | 17301000 | AED | 72 | 2026-08-20
PRJ-1011 | Next-Gen SIEM Rollout | Cloud-native SIEM with curated healthcare detection content replacing the end-of-life platform. | Cybersecurity | Resilience & Security | Fortress | PRJ-1010 | Aisha Al Hammadi | Amna Al Ali | Splunk | In Progress | Green | Medium | Monitoring | 2026-03-02 | 2026-04-15 | 2027-11-23 |  | 14150000 | 10237000 | AED | 80 | 2026-07-23
PRJ-1012 | Zero Trust Network Access | Identity-aware access replacing legacy VPN for workforce, third parties and remote clinicians. | Cybersecurity | Resilience & Security | Fortress | PRJ-1010 | Ravi Subramanian | Catherine Dubois | Cisco | In Progress | Green | Low | Monitoring | 2025-04-26 | 2025-06-26 | 2026-09-23 |  | 2400000 | 2199000 | AED | 90 | 2026-08-15
PRJ-1013 | Medical Device Security (IoMT) | Discovery, segmentation and monitoring of connected medical devices across clinical networks. | Cybersecurity | Resilience & Security | Fortress | PRJ-1010 | Grace Okafor | Saif Al Dhaheri | Cisco | In Progress | Red | High | Execution | 2025-04-09 | 2025-05-19 | 2026-07-15 |  | 6150000 | 3949000 | AED | 58 | 2026-08-01
PRJ-1014 | Privileged Access Management | Vaulting, session recording and just-in-time elevation for all privileged accounts. | Cybersecurity | Resilience & Security | Fortress | PRJ-1010 | Fatima Al Zaabi | Saif Al Dhaheri | IBM Consulting | Completed | Green | Medium | Closure | 2024-12-10 | 2025-01-02 | 2026-06-05 | 2026-06-12 | 7700000 | 7885000 | AED | 100 | 2026-08-03
PRJ-1015 | 24x7 SOC Managed Detection & Response | Co-managed security operations center with round-the-clock monitoring and incident response. | Cybersecurity | Resilience & Security | Fortress | PRJ-1010 | Ahmed Al Mansoori | Amna Al Ali | e& enterprise | In Progress | Green | Medium | Monitoring | 2024-09-01 | 2024-11-26 | 2027-01-25 |  | 3050000 | 2070000 | AED | 83 | 2026-08-04
PRJ-1020 | Insight Data & AI Program | Umbrella program building the enterprise data platform and scaling responsible clinical AI. | Data & AI | Intelligent Enterprise | Insight |  | Ravi Subramanian | Catherine Dubois | Microsoft | In Progress | Green | Critical | Execution | 2024-12-19 | 2025-01-13 | 2027-06-30 |  | 24000000 | 11623000 | AED | 45 | 2026-08-12
PRJ-1021 | Enterprise Data Lakehouse | Unified lakehouse consolidating clinical, operational and financial data with governed access. | Data & AI | Intelligent Enterprise | Insight | PRJ-1020 | Aisha Al Hammadi | Mohammed Al Hashimi | Microsoft | In Progress | Amber | Medium | Execution | 2025-08-18 | 2025-09-05 | 2027-01-04 |  | 12300000 | 7495000 | AED | 67 | 2026-07-28
PRJ-1022 | Clinical AI Decision Support Pilots | Sepsis early-warning and radiology worklist prioritization pilots under clinical governance. | Data & AI | Patient-Centric Care | Insight | PRJ-1020 | Daniel Weber | Saif Al Dhaheri | GE HealthCare | Approved | Green | Medium | Planning | 2026-08-18 | 2026-09-07 | 2027-10-11 |  | 4850000 | 123000 | AED | 7 | 2026-08-20
PRJ-1023 | Population Health Analytics | Risk stratification and chronic disease registries to support proactive outreach programs. | Data & AI | Patient-Centric Care | Insight | PRJ-1020 | Mariam Al Suwaidi | Dr. Hessa Al Falasi | AWS | Proposed | Green | Medium | Initiation |  | 2026-09-25 | 2027-05-12 |  | 2950000 | 0 | AED | 0 | 2026-08-05
PRJ-1024 | Master Patient Index Remediation | Duplicate record resolution and probabilistic matching uplift for a trusted patient identity. | Data & AI | Operational Excellence | Insight | PRJ-1020 | Li Wei Chen | Catherine Dubois | IBM Consulting | Completed | Green | Critical | Closure | 2024-12-23 | 2025-02-13 | 2026-06-15 | 2026-05-28 | 6850000 | 6164000 | AED | 100 | 2026-08-13
PRJ-1030 | Horizon Cloud & ERP Program | Umbrella program moving corporate systems to cloud ERP and exiting the primary data center. | ERP & Corporate Systems | Intelligent Enterprise | Horizon |  | Saeed Al Falahi | Saif Al Dhaheri | SAP | In Progress | Amber | Critical | Execution | 2024-03-17 | 2024-06-10 | 2026-11-30 |  | 38000000 | 19838000 | AED | 63 | 2026-08-10
PRJ-1031 | ERP Cloud Migration (Finance & Supply Chain) | Greenfield S/4HANA implementation for finance, procurement and supply chain with data conversion. | ERP & Corporate Systems | Intelligent Enterprise | Horizon | PRJ-1030 | Sara Haddad | Dr. Hessa Al Falasi | SAP | In Progress | Red | Critical | Execution | 2024-11-29 | 2025-01-28 | 2026-07-31 |  | 18200000 | 20081000 | AED | 71 | 2026-08-23
PRJ-1032 | HR & Payroll Cloud Transition | SuccessFactors core HR, payroll and self-service rollout for 12,000 employees. | ERP & Corporate Systems | Operational Excellence | Horizon | PRJ-1030 | Noura Al Kaabi | Dr. Vandana Sharma | SAP | Completed | Green | High | Closure | 2025-01-01 | 2025-03-07 | 2026-08-31 | 2026-08-21 | 2250000 | 2299000 | AED | 100 | 2026-08-22
PRJ-1033 | Data Center Exit & Cloud Landing Zone | Secure landing zone, migration factory and decommissioning plan for the primary data center. | ERP & Corporate Systems | Resilience & Security | Horizon | PRJ-1030 | James O'Connor | Mohammed Al Hashimi | AWS | In Progress | Amber | High | Execution | 2025-06-22 | 2025-09-08 | 2027-03-15 |  | 15550000 | 9373000 | AED | 58 | 2026-08-15
PRJ-1034 | Integration Platform (iPaaS) Buildout | Enterprise integration platform replacing point-to-point interfaces with governed APIs. | ERP & Corporate Systems | Intelligent Enterprise | Horizon | PRJ-1030 | Omar Al Shamsi | Eng. Salem Al Nuaimi | Microsoft | In Progress | Green | Medium | Execution | 2025-06-22 | 2025-07-21 | 2026-11-10 |  | 6300000 | 3851000 | AED | 73 | 2026-07-18
PRJ-1040 | Aman Patient App 2.0 | Next-generation patient app: appointments, results, payments and virtual queue in one journey. | Patient Experience | Patient-Centric Care |  |  | James O'Connor | Catherine Dubois | Accenture | In Progress | Green | Low | Execution | 2025-06-30 | 2025-09-20 | 2026-12-09 |  | 14700000 | 8086000 | AED | 58 | 2026-08-03
PRJ-1041 | Telehealth Expansion Wave 3 | Extending virtual consultations to dermatology, mental health and post-surgical follow-up. | Digital Health | Patient-Centric Care |  |  | Fatima Al Zaabi | Eng. Salem Al Nuaimi | Philips | In Progress | Green | Low | Execution | 2025-06-13 | 2025-08-24 | 2027-02-11 |  | 5650000 | 3469000 | AED | 55 | 2026-07-16
PRJ-1042 | Contact Center AI Virtual Agent | Arabic/English conversational AI deflecting routine calls and booking appointments end to end. | Patient Experience | Intelligent Enterprise |  |  | Yusuf Khan | Amna Al Ali | Genesys | In Progress | Amber | High | Execution | 2025-12-17 | 2026-02-28 | 2026-11-09 |  | 3750000 | 2425000 | AED | 68 | 2026-08-22
PRJ-1043 | Clinical Network Segmentation | Micro-segmentation of clinical VLANs isolating biomedical, guest and corporate traffic. | Network & Telecom | Resilience & Security |  |  | Priya Nair | Mohammed Al Hashimi | Cisco | On Hold | Amber | Low | Planning | 2025-09-27 | 2025-11-11 | 2026-12-19 |  | 7400000 | 2331000 | AED | 33 | 2026-07-29
PRJ-1044 | Hospital Wi-Fi 6E Refresh | Campus-wide wireless refresh for clinical mobility, RTLS readiness and guest services. | Network & Telecom | Operational Excellence |  |  | Yusuf Khan | Catherine Dubois | Cisco | Completed | Green | Medium | Closure | 2025-03-31 | 2025-06-04 | 2026-07-20 | 2026-07-29 | 2250000 | 2164000 | AED | 100 | 2026-08-04
PRJ-1045 | RIS/PACS Upgrade & Vendor-Neutral Archive | Radiology platform upgrade with a vendor-neutral archive consolidating enterprise imaging. | Digital Health | Digital Transformation |  |  | Aisha Al Hammadi | Eng. Salem Al Nuaimi | GE HealthCare | In Progress | Green | Medium | Execution | 2025-02-02 | 2025-03-17 | 2027-04-04 |  | 14200000 | 8580000 | AED | 58 | 2026-07-20
PRJ-1046 | Pharmacy Automation Robotics Integration | Robotic dispensing integration cancelled after vendor exit from the regional market. | Digital Health | Operational Excellence |  |  | Mariam Al Suwaidi | Eng. Salem Al Nuaimi | Philips | Cancelled | Amber | Medium | Closure | 2025-06-22 | 2025-08-10 | 2026-07-11 |  | 6000000 | 353000 | AED | 7 | 2026-08-21
PRJ-1047 | SD-WAN for Remote Clinics | Resilient software-defined WAN with local breakout for 23 remote clinics and field units. | Network & Telecom | Resilience & Security |  |  | Mariam Al Suwaidi | Catherine Dubois | Cisco | In Progress | Green | Medium | Execution | 2025-01-08 | 2025-03-15 | 2026-10-12 |  | 4500000 | 2664000 | AED | 70 | 2026-08-04
PRJ-1048 | Endpoint Modernization (Windows 11) | Fleet refresh and zero-touch provisioning for 9,500 clinical and corporate endpoints. | Cloud & Infrastructure | Operational Excellence |  |  | Saeed Al Falahi | Mohammed Al Hashimi | Dell Technologies | In Progress | Green | Medium | Execution | 2024-08-24 | 2024-11-09 | 2026-12-24 |  | 6600000 | 3751000 | AED | 71 | 2026-07-17
PRJ-1049 | Disaster Recovery as a Service | Cloud-based DR for tier-1 clinical systems with automated failover runbooks and testing. | Cloud & Infrastructure | Resilience & Security |  |  | Li Wei Chen | Dr. Richard Hughes | AWS | Approved | Green | Critical | Planning | 2026-08-20 | 2026-09-14 | 2027-05-15 |  | 6300000 | 101000 | AED | 4 | 2026-08-22
PRJ-1050 | Patient Flow RTLS | Real-time location services for patient flow, asset tracking and bed turnover analytics. | Patient Experience | Operational Excellence |  |  | Sara Haddad | Catherine Dubois | Philips | On Hold | Red | High | Planning | 2025-09-28 | 2025-12-15 | 2027-03-01 |  | 3700000 | 896000 | AED | 28 | 2026-07-31
PRJ-1051 | Procurement Punch-Out & e-Invoicing | Supplier punch-out catalogs and UAE e-invoicing compliance for the procure-to-pay cycle. | ERP & Corporate Systems | Operational Excellence |  |  | Ahmed Al Mansoori | Mohammed Al Hashimi | Genesys | Proposed | Green | Medium | Initiation |  | 2026-10-21 | 2027-11-27 |  | 650000 | 0 | AED | 3 | 2026-07-20

## Milestones
Project ID | Name | Due Date | Completed Date | Status
PRJ-1001 | Vendor Contract Signed | 2024-09-04 | 2024-09-10 | Completed
PRJ-1001 | Solution Design Sign-off | 2025-03-04 | 2025-03-06 | Completed
PRJ-1001 | Environment Provisioning Complete | 2025-08-24 | 2025-09-01 | Completed
PRJ-1001 | Data Migration Dry Run | 2026-02-23 | 2026-02-18 | Completed
PRJ-1001 | Pilot Go-Live | 2026-08-18 |  | Overdue
PRJ-1001 | Hypercare Exit | 2027-01-29 |  | In Progress
PRJ-1002 | Integration Testing Complete | 2025-07-07 | 2025-07-07 | Completed
PRJ-1002 | UAT Sign-off | 2025-11-25 | 2025-11-24 | Completed
PRJ-1002 | Training & Adoption Complete | 2026-04-16 | 2026-04-11 | Completed
PRJ-1002 | Go/No-Go Readiness Review | 2026-08-22 | 2026-08-16 | Completed
PRJ-1002 | Benefits Review | 2026-09-07 |  | Pending
PRJ-1003 | Business Case Approved | 2025-05-18 | 2025-05-16 | Completed
PRJ-1003 | Environment Provisioning Complete | 2025-08-13 | 2025-08-10 | Completed
PRJ-1003 | Integration Testing Complete | 2025-10-25 | 2025-10-22 | Completed
PRJ-1003 | UAT Sign-off | 2026-01-05 | 2026-01-06 | Completed
PRJ-1003 | Training & Adoption Complete | 2026-03-25 | 2026-03-29 | Completed
PRJ-1003 | Benefits Review | 2026-06-08 |  | Overdue
PRJ-1004 | Security & Compliance Review | 2025-11-28 | 2025-11-21 | Completed
PRJ-1004 | UAT Sign-off | 2026-03-13 | 2026-03-08 | Completed
PRJ-1004 | Pilot Go-Live | 2026-07-08 | 2026-07-02 | Completed
PRJ-1005 | Business Case Approved | 2025-08-26 | 2025-08-25 | Completed
PRJ-1005 | Vendor Contract Signed | 2025-11-22 | 2025-11-24 | Completed
PRJ-1005 | Integration Testing Complete | 2026-02-17 | 2026-02-13 | Completed
PRJ-1005 | Pilot Go-Live | 2026-04-24 |  | Overdue
PRJ-1005 | Training & Adoption Complete | 2026-07-28 |  | Overdue
PRJ-1005 | Production Go-Live | 2026-10-05 |  | In Progress
PRJ-1006 | Vendor Contract Signed | 2027-01-19 |  | Pending
PRJ-1006 | UAT Sign-off | 2027-05-08 |  | Pending
PRJ-1006 | Pilot Go-Live | 2027-09-03 |  | Pending
PRJ-1010 | Vendor Contract Signed | 2025-02-17 | 2025-02-25 | Completed
PRJ-1010 | Environment Provisioning Complete | 2025-07-22 | 2025-07-29 | Completed
PRJ-1010 | Data Migration Dry Run | 2025-12-17 | 2025-12-13 | Completed
PRJ-1010 | Production Go-Live | 2026-05-27 | 2026-05-25 | Completed
PRJ-1010 | Hypercare Exit | 2026-11-14 |  | Pending
PRJ-1011 | Go/No-Go Readiness Review | 2026-08-27 |  | Pending
PRJ-1011 | Environment Provisioning Complete | 2026-10-17 |  | In Progress
PRJ-1011 | Integration Testing Complete | 2027-04-13 |  | Pending
PRJ-1011 | Benefits Review | 2027-10-04 |  | Pending
PRJ-1012 | Business Case Approved | 2025-09-15 | 2025-09-14 | Completed
PRJ-1012 | Solution Design Sign-off | 2025-11-11 | 2025-11-05 | Completed
PRJ-1012 | Data Migration Dry Run | 2026-01-28 | 2026-01-30 | Completed
PRJ-1012 | Integration Testing Complete | 2026-04-03 | 2026-03-30 | Completed
PRJ-1012 | Security & Compliance Review | 2026-06-28 | 2026-06-29 | Completed
PRJ-1012 | Pilot Go-Live | 2026-09-07 |  | Pending
PRJ-1013 | Vendor Contract Signed | 2025-08-03 | 2025-08-07 | Completed
PRJ-1013 | Pilot Go-Live | 2025-11-01 | 2025-11-02 | Completed
PRJ-1013 | Training & Adoption Complete | 2026-01-06 | 2026-01-12 | Completed
PRJ-1013 | Production Go-Live | 2026-03-27 |  | Overdue
PRJ-1013 | Hypercare Exit | 2026-06-19 | 2026-06-23 | Completed
PRJ-1014 | UAT Sign-off | 2025-06-15 | 2025-06-17 | Completed
PRJ-1014 | Training & Adoption Complete | 2025-11-14 | 2025-11-10 | Completed
PRJ-1014 | Hypercare Exit | 2026-04-23 | 2026-04-26 | Completed
PRJ-1015 | Vendor Contract Signed | 2025-05-23 | 2025-05-31 | Completed
PRJ-1015 | Solution Design Sign-off | 2025-12-08 | 2025-12-13 | Completed
PRJ-1015 | Data Migration Dry Run | 2026-05-25 | 2026-05-31 | Completed
PRJ-1015 | Integration Testing Complete | 2026-12-04 |  | Pending
PRJ-1020 | Vendor Contract Signed | 2025-06-02 | 2025-06-01 | Completed
PRJ-1020 | Environment Provisioning Complete | 2025-10-31 | 2025-10-28 | Completed
PRJ-1020 | UAT Sign-off | 2026-03-10 | 2026-03-14 | Completed
PRJ-1020 | Training & Adoption Complete | 2026-08-07 | 2026-08-08 | Completed
PRJ-1020 | Hypercare Exit | 2026-12-29 |  | In Progress
PRJ-1020 | Benefits Review | 2027-05-17 |  | Pending
PRJ-1021 | Business Case Approved | 2025-11-30 | 2025-11-27 | Completed
PRJ-1021 | Vendor Contract Signed | 2026-02-13 | 2026-02-12 | Completed
PRJ-1021 | Solution Design Sign-off | 2026-04-27 |  | Overdue
PRJ-1021 | Environment Provisioning Complete | 2026-06-30 | 2026-06-27 | Completed
PRJ-1021 | Go/No-Go Readiness Review | 2026-08-29 |  | Pending
PRJ-1021 | Training & Adoption Complete | 2026-09-29 |  | Pending
PRJ-1021 | Benefits Review | 2026-12-17 |  | Pending
PRJ-1022 | Business Case Approved | 2027-01-01 |  | Pending
PRJ-1022 | Integration Testing Complete | 2027-04-30 |  | Pending
PRJ-1022 | Production Go-Live | 2027-09-12 |  | Pending
PRJ-1023 | Business Case Approved | 2026-11-23 |  | Pending
PRJ-1023 | Vendor Contract Signed | 2027-01-18 |  | Pending
PRJ-1023 | UAT Sign-off | 2027-03-09 |  | Pending
PRJ-1023 | Benefits Review | 2027-04-28 |  | Pending
PRJ-1024 | Data Migration Dry Run | 2025-04-21 | 2025-04-19 | Completed
PRJ-1024 | Integration Testing Complete | 2025-07-05 | 2025-06-30 | Completed
PRJ-1024 | Security & Compliance Review | 2025-09-17 | 2025-09-19 | Completed
PRJ-1024 | UAT Sign-off | 2025-12-09 | 2025-12-04 | Completed
PRJ-1024 | Pilot Go-Live | 2026-02-16 | 2026-02-16 | Completed
PRJ-1024 | Production Go-Live | 2026-05-04 | 2026-05-02 | Completed
PRJ-1030 | Vendor Contract Signed | 2025-03-19 | 2025-03-22 | Completed
PRJ-1030 | Training & Adoption Complete | 2025-12-06 | 2025-12-10 | Completed
PRJ-1030 | Benefits Review | 2026-09-14 |  | In Progress
PRJ-1031 | Solution Design Sign-off | 2025-04-28 | 2025-05-05 | Completed
PRJ-1031 | Environment Provisioning Complete | 2025-07-26 | 2025-07-29 | Completed
PRJ-1031 | Data Migration Dry Run | 2025-10-07 | 2025-10-01 | Completed
PRJ-1031 | Integration Testing Complete | 2026-01-17 | 2026-01-12 | Completed
PRJ-1031 | UAT Sign-off | 2026-04-09 |  | Overdue
PRJ-1031 | Benefits Review | 2026-07-11 | 2026-07-05 | Completed
PRJ-1032 | Business Case Approved | 2025-06-09 | 2025-06-14 | Completed
PRJ-1032 | Solution Design Sign-off | 2025-08-18 | 2025-08-16 | Completed
PRJ-1032 | Data Migration Dry Run | 2025-11-17 | 2025-11-21 | Completed
PRJ-1032 | Integration Testing Complete | 2026-02-15 | 2026-02-18 | Completed
PRJ-1032 | UAT Sign-off | 2026-05-07 | 2026-05-10 | Completed
PRJ-1032 | Benefits Review | 2026-08-02 | 2026-07-29 | Completed
PRJ-1033 | Business Case Approved | 2025-11-26 | 2025-11-23 | Completed
PRJ-1033 | Vendor Contract Signed | 2026-03-06 | 2026-03-09 | Completed
PRJ-1033 | Environment Provisioning Complete | 2026-05-28 |  | Overdue
PRJ-1033 | UAT Sign-off | 2026-08-30 |  | In Progress
PRJ-1033 | Hypercare Exit | 2026-11-16 |  | Pending
PRJ-1033 | Benefits Review | 2027-02-08 |  | Pending
PRJ-1034 | Business Case Approved | 2025-09-26 | 2025-09-21 | Completed
PRJ-1034 | Environment Provisioning Complete | 2025-12-16 | 2025-12-11 | Completed
PRJ-1034 | Data Migration Dry Run | 2026-02-24 | 2026-03-03 | Completed
PRJ-1034 | Security & Compliance Review | 2026-05-10 | 2026-05-15 | Completed
PRJ-1034 | Training & Adoption Complete | 2026-08-02 | 2026-07-27 | Completed
PRJ-1034 | Production Go-Live | 2026-10-22 |  | In Progress
PRJ-1040 | Business Case Approved | 2025-12-02 | 2025-12-07 | Completed
PRJ-1040 | Solution Design Sign-off | 2026-02-27 | 2026-03-07 | Completed
PRJ-1040 | Environment Provisioning Complete | 2026-05-22 | 2026-05-26 | Completed
PRJ-1040 | Integration Testing Complete | 2026-08-22 | 2026-08-23 | Completed
PRJ-1040 | Go/No-Go Readiness Review | 2026-08-25 |  | In Progress
PRJ-1040 | Hypercare Exit | 2026-11-09 |  | Pending
PRJ-1041 | Business Case Approved | 2025-11-10 | 2025-11-15 | Completed
PRJ-1041 | Vendor Contract Signed | 2026-02-07 | 2026-02-01 | Completed
PRJ-1041 | Integration Testing Complete | 2026-04-30 | 2026-04-27 | Completed
PRJ-1041 | UAT Sign-off | 2026-07-22 | 2026-07-16 | Completed
PRJ-1041 | Training & Adoption Complete | 2026-10-21 |  | In Progress
PRJ-1041 | Benefits Review | 2027-01-23 |  | Pending
PRJ-1042 | Vendor Contract Signed | 2026-04-18 |  | Overdue
PRJ-1042 | Solution Design Sign-off | 2026-05-16 |  | Overdue
PRJ-1042 | UAT Sign-off | 2026-06-28 | 2026-06-28 | Completed
PRJ-1042 | Pilot Go-Live | 2026-08-18 | 2026-08-23 | Completed
PRJ-1042 | Hypercare Exit | 2026-09-19 |  | In Progress
PRJ-1042 | Benefits Review | 2026-10-24 |  | Pending
PRJ-1043 | Solution Design Sign-off | 2026-01-21 | 2026-01-15 | Completed
PRJ-1043 | Environment Provisioning Complete | 2026-04-11 |  | Overdue
PRJ-1043 | Data Migration Dry Run | 2026-06-18 |  | Overdue
PRJ-1043 | Training & Adoption Complete | 2026-09-12 |  | Pending
PRJ-1043 | Hypercare Exit | 2026-11-27 |  | Pending
PRJ-1044 | Vendor Contract Signed | 2025-08-15 | 2025-08-16 | Completed
PRJ-1044 | Data Migration Dry Run | 2025-10-21 | 2025-10-26 | Completed
PRJ-1044 | Integration Testing Complete | 2025-12-22 | 2025-12-17 | Completed
PRJ-1044 | Training & Adoption Complete | 2026-02-25 | 2026-03-02 | Completed
PRJ-1044 | Production Go-Live | 2026-05-06 | 2026-04-29 | Completed
PRJ-1044 | Hypercare Exit | 2026-07-09 | 2026-07-06 | Completed
PRJ-1045 | Business Case Approved | 2025-07-19 | 2025-07-21 | Completed
PRJ-1045 | Vendor Contract Signed | 2025-11-14 | 2025-11-21 | Completed
PRJ-1045 | Environment Provisioning Complete | 2026-02-26 | 2026-03-06 | Completed
PRJ-1045 | Security & Compliance Review | 2026-07-13 | 2026-07-10 | Completed
PRJ-1045 | Pilot Go-Live | 2026-11-08 |  | Pending
PRJ-1045 | Production Go-Live | 2027-03-02 |  | In Progress
PRJ-1046 | Data Migration Dry Run | 2025-10-18 | 2025-10-15 | Completed
PRJ-1046 | Integration Testing Complete | 2026-01-22 | 2026-01-17 | Completed
PRJ-1046 | Training & Adoption Complete | 2026-03-23 | 2026-03-31 | Completed
PRJ-1046 | Hypercare Exit | 2026-06-17 | 2026-06-18 | Completed
PRJ-1047 | Data Migration Dry Run | 2025-06-24 | 2025-06-25 | Completed
PRJ-1047 | Integration Testing Complete | 2025-09-05 | 2025-08-31 | Completed
PRJ-1047 | UAT Sign-off | 2025-12-12 | 2025-12-18 | Completed
PRJ-1047 | Pilot Go-Live | 2026-03-09 | 2026-03-13 | Completed
PRJ-1047 | Hypercare Exit | 2026-06-07 | 2026-06-12 | Completed
PRJ-1047 | Benefits Review | 2026-09-24 |  | In Progress
PRJ-1048 | Business Case Approved | 2025-04-01 | 2025-03-26 | Completed
PRJ-1048 | Data Migration Dry Run | 2025-08-21 | 2025-08-24 | Completed
PRJ-1048 | Security & Compliance Review | 2026-01-29 | 2026-01-31 | Completed
PRJ-1048 | Pilot Go-Live | 2026-06-11 | 2026-06-17 | Completed
PRJ-1048 | Hypercare Exit | 2026-11-17 |  | In Progress
PRJ-1049 | Vendor Contract Signed | 2026-11-04 |  | Pending
PRJ-1049 | Solution Design Sign-off | 2026-12-18 |  | Pending
PRJ-1049 | Data Migration Dry Run | 2027-02-06 |  | Pending
PRJ-1049 | Training & Adoption Complete | 2027-03-15 |  | Pending
PRJ-1049 | Production Go-Live | 2027-05-08 |  | Pending
PRJ-1050 | Solution Design Sign-off | 2026-02-26 | 2026-03-02 | Completed
PRJ-1050 | Security & Compliance Review | 2026-06-09 |  | Overdue
PRJ-1050 | UAT Sign-off | 2026-08-16 | 2026-08-14 | Completed
PRJ-1050 | Hypercare Exit | 2026-11-10 |  | Pending
PRJ-1050 | Benefits Review | 2027-02-12 |  | Pending
PRJ-1051 | Integration Testing Complete | 2026-12-21 |  | Pending
PRJ-1051 | Security & Compliance Review | 2027-03-03 |  | Pending
PRJ-1051 | UAT Sign-off | 2027-05-04 |  | Pending
PRJ-1051 | Pilot Go-Live | 2027-07-05 |  | Pending
PRJ-1051 | Training & Adoption Complete | 2027-09-13 |  | Pending
PRJ-1051 | Hypercare Exit | 2027-11-13 |  | Pending

## Updates
Project ID | Date | Author | Text
PRJ-1001 | 2026-07-24 | Fatima Al Zaabi | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1001 | 2026-08-01 | Fatima Al Zaabi | Sprint review complete; delivery tracking at 68% with the critical path stable.
PRJ-1001 | 2026-08-21 | Fatima Al Zaabi | Steering committee endorsed the revised integration plan; Epic Systems has committed additional senior resources.
PRJ-1002 | 2026-07-10 | Ravi Subramanian | Steering committee endorsed the revised integration plan; Epic Systems has committed additional senior resources.
PRJ-1002 | 2026-07-25 | Ravi Subramanian | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1002 | 2026-08-13 | Ravi Subramanian | Executive walkthrough delivered to the sponsor; Ravi Subramanian confirmed no change to the committed scope.
PRJ-1003 | 2026-08-02 | Khalid Al Marzooqi | Steering committee endorsed the revised integration plan; Accenture has committed additional senior resources.
PRJ-1003 | 2026-08-20 | Khalid Al Marzooqi | Recovery plan invoked: scope re-sequenced, weekly CIO checkpoint established, and Accenture penalties under review.
PRJ-1004 | 2026-06-28 | Mariam Al Suwaidi | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-1004 | 2026-07-15 | Mariam Al Suwaidi | Executive walkthrough delivered to the sponsor; Mariam Al Suwaidi confirmed no change to the committed scope.
PRJ-1004 | 2026-08-04 | Mariam Al Suwaidi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1004 | 2026-08-20 | Mariam Al Suwaidi | Closure report approved by the steering committee; residual actions handed to operations with owners and dates.
PRJ-1005 | 2026-07-04 | Daniel Weber | Steering committee endorsed the revised integration plan; Epic Systems has committed additional senior resources.
PRJ-1005 | 2026-07-19 | Daniel Weber | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1006 | 2026-07-05 | Omar Al Shamsi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1006 | 2026-07-15 | Omar Al Shamsi | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1006 | 2026-08-02 | Omar Al Shamsi | Mobilization underway: delivery manager assigned, vendor SOW in legal review, and kickoff scheduled.
PRJ-1010 | 2026-08-11 | Khalid Al Marzooqi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1010 | 2026-08-20 | Khalid Al Marzooqi | Executive walkthrough delivered to the sponsor; Khalid Al Marzooqi confirmed no change to the committed scope.
PRJ-1011 | 2026-07-07 | Aisha Al Hammadi | Sprint review complete; delivery tracking at 80% with the critical path stable.
PRJ-1011 | 2026-07-23 | Aisha Al Hammadi | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1012 | 2026-07-10 | Ravi Subramanian | Steering committee endorsed the revised integration plan; Cisco has committed additional senior resources.
PRJ-1012 | 2026-07-28 | Ravi Subramanian | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-1012 | 2026-08-15 | Ravi Subramanian | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-1013 | 2026-07-12 | Grace Okafor | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-1013 | 2026-08-01 | Grace Okafor | Recovery plan invoked: scope re-sequenced, weekly CIO checkpoint established, and Cisco penalties under review.
PRJ-1014 | 2026-06-27 | Fatima Al Zaabi | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1014 | 2026-07-08 | Fatima Al Zaabi | Sprint review complete; delivery tracking at 100% with the critical path stable.
PRJ-1014 | 2026-07-23 | Fatima Al Zaabi | Executive walkthrough delivered to the sponsor; Fatima Al Zaabi confirmed no change to the committed scope.
PRJ-1014 | 2026-08-03 | Fatima Al Zaabi | Closure report approved by the steering committee; residual actions handed to operations with owners and dates.
PRJ-1015 | 2026-07-02 | Ahmed Al Mansoori | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1015 | 2026-07-21 | Ahmed Al Mansoori | Executive walkthrough delivered to the sponsor; Ahmed Al Mansoori confirmed no change to the committed scope.
PRJ-1015 | 2026-08-04 | Ahmed Al Mansoori | Sprint review complete; delivery tracking at 83% with the critical path stable.
PRJ-1020 | 2026-07-03 | Ravi Subramanian | Executive walkthrough delivered to the sponsor; Ravi Subramanian confirmed no change to the committed scope.
PRJ-1020 | 2026-07-23 | Ravi Subramanian | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-1020 | 2026-08-04 | Ravi Subramanian | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1020 | 2026-08-12 | Ravi Subramanian | Executive walkthrough delivered to the sponsor; Ravi Subramanian confirmed no change to the committed scope.
PRJ-1021 | 2026-07-10 | Aisha Al Hammadi | Executive walkthrough delivered to the sponsor; Aisha Al Hammadi confirmed no change to the committed scope.
PRJ-1021 | 2026-07-28 | Aisha Al Hammadi | Executive walkthrough delivered to the sponsor; Aisha Al Hammadi confirmed no change to the committed scope.
PRJ-1022 | 2026-06-30 | Daniel Weber | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-1022 | 2026-07-13 | Daniel Weber | Executive walkthrough delivered to the sponsor; Daniel Weber confirmed no change to the committed scope.
PRJ-1022 | 2026-07-24 | Daniel Weber | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-1022 | 2026-08-03 | Daniel Weber | Sprint review complete; delivery tracking at 7% with the critical path stable.
PRJ-1022 | 2026-08-20 | Daniel Weber | Funding released by the Digital Investment Committee; resource onboarding and environment requests initiated.
PRJ-1023 | 2026-07-28 | Mariam Al Suwaidi | Executive walkthrough delivered to the sponsor; Mariam Al Suwaidi confirmed no change to the committed scope.
PRJ-1023 | 2026-08-05 | Mariam Al Suwaidi | Business case refined with Finance; TCO validated and submitted to the Digital Investment Committee.
PRJ-1024 | 2026-06-28 | Li Wei Chen | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-1024 | 2026-07-07 | Li Wei Chen | Sprint review complete; delivery tracking at 100% with the critical path stable.
PRJ-1024 | 2026-07-24 | Li Wei Chen | Sprint review complete; delivery tracking at 100% with the critical path stable.
PRJ-1024 | 2026-08-13 | Li Wei Chen | Project formally closed. Hypercare exited with zero Sev-1 incidents; benefits realization transferred to the service owner.
PRJ-1030 | 2026-07-25 | Saeed Al Falahi | Sprint review complete; delivery tracking at 63% with the critical path stable.
PRJ-1030 | 2026-08-10 | Saeed Al Falahi | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1031 | 2026-07-27 | Sara Haddad | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1031 | 2026-08-07 | Sara Haddad | Recovery plan invoked: scope re-sequenced, weekly CIO checkpoint established, and SAP penalties under review.
PRJ-1031 | 2026-08-23 | Sara Haddad | Escalation: data quality remains below the migration threshold; a joint remediation cell has been stood up.
PRJ-1032 | 2026-07-03 | Noura Al Kaabi | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1032 | 2026-07-16 | Noura Al Kaabi | Executive walkthrough delivered to the sponsor; Noura Al Kaabi confirmed no change to the committed scope.
PRJ-1032 | 2026-08-03 | Noura Al Kaabi | Sprint review complete; delivery tracking at 100% with the critical path stable.
PRJ-1032 | 2026-08-22 | Noura Al Kaabi | Closure report approved by the steering committee; residual actions handed to operations with owners and dates.
PRJ-1033 | 2026-07-28 | James O'Connor | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1033 | 2026-08-15 | James O'Connor | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-1034 | 2026-06-29 | Omar Al Shamsi | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-1034 | 2026-07-18 | Omar Al Shamsi | Sprint review complete; delivery tracking at 73% with the critical path stable.
PRJ-1040 | 2026-06-27 | James O'Connor | Sprint review complete; delivery tracking at 58% with the critical path stable.
PRJ-1040 | 2026-07-16 | James O'Connor | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1040 | 2026-08-03 | James O'Connor | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-1041 | 2026-07-01 | Fatima Al Zaabi | Sprint review complete; delivery tracking at 55% with the critical path stable.
PRJ-1041 | 2026-07-16 | Fatima Al Zaabi | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-1042 | 2026-07-20 | Yusuf Khan | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-1042 | 2026-08-09 | Yusuf Khan | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1042 | 2026-08-22 | Yusuf Khan | Steering committee endorsed the revised integration plan; Genesys has committed additional senior resources.
PRJ-1043 | 2026-06-25 | Priya Nair | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-1043 | 2026-07-14 | Priya Nair | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1043 | 2026-07-29 | Priya Nair | Initiative paused pending vendor contract renegotiation; restart criteria agreed with the sponsor.
PRJ-1044 | 2026-07-14 | Yusuf Khan | Steering committee endorsed the revised integration plan; Cisco has committed additional senior resources.
PRJ-1044 | 2026-07-25 | Yusuf Khan | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1044 | 2026-08-04 | Yusuf Khan | Closure report approved by the steering committee; residual actions handed to operations with owners and dates.
PRJ-1045 | 2026-06-25 | Aisha Al Hammadi | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-1045 | 2026-07-07 | Aisha Al Hammadi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1045 | 2026-07-20 | Aisha Al Hammadi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1046 | 2026-08-01 | Mariam Al Suwaidi | Sprint review complete; delivery tracking at 7% with the critical path stable.
PRJ-1046 | 2026-08-21 | Mariam Al Suwaidi | Initiative cancelled following portfolio rebalancing; residual commitments settled and lessons captured.
PRJ-1047 | 2026-07-03 | Mariam Al Suwaidi | Steering committee endorsed the revised integration plan; Cisco has committed additional senior resources.
PRJ-1047 | 2026-07-15 | Mariam Al Suwaidi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1047 | 2026-08-04 | Mariam Al Suwaidi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-1048 | 2026-07-06 | Saeed Al Falahi | Executive walkthrough delivered to the sponsor; Saeed Al Falahi confirmed no change to the committed scope.
PRJ-1048 | 2026-07-17 | Saeed Al Falahi | Sprint review complete; delivery tracking at 71% with the critical path stable.
PRJ-1049 | 2026-07-05 | Li Wei Chen | Executive walkthrough delivered to the sponsor; Li Wei Chen confirmed no change to the committed scope.
PRJ-1049 | 2026-07-25 | Li Wei Chen | Executive walkthrough delivered to the sponsor; Li Wei Chen confirmed no change to the committed scope.
PRJ-1049 | 2026-08-07 | Li Wei Chen | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-1049 | 2026-08-22 | Li Wei Chen | Funding released by the Digital Investment Committee; resource onboarding and environment requests initiated.
PRJ-1050 | 2026-07-04 | Sara Haddad | Escalation: data quality remains below the migration threshold; a joint remediation cell has been stood up.
PRJ-1050 | 2026-07-17 | Sara Haddad | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-1050 | 2026-07-31 | Sara Haddad | On hold at the portfolio board's direction while enterprise architecture completes the platform review.
PRJ-1051 | 2026-06-30 | Ahmed Al Mansoori | Executive walkthrough delivered to the sponsor; Ahmed Al Mansoori confirmed no change to the committed scope.
PRJ-1051 | 2026-07-08 | Ahmed Al Mansoori | Executive walkthrough delivered to the sponsor; Ahmed Al Mansoori confirmed no change to the committed scope.
PRJ-1051 | 2026-07-20 | Ahmed Al Mansoori | Business case refined with Finance; TCO validated and submitted to the Digital Investment Committee.

## Risks
Project ID | Title | Severity | Status | Owner
PRJ-1001 | Third-party API instability in production | Low | Open | Li Wei Chen
PRJ-1001 | Cutover rollback plan untested at scale | Medium | Mitigating | Sara Haddad
PRJ-1003 | Regulatory compliance deadline (DoH/NESA) slippage | Critical | Open | Daniel Weber
PRJ-1003 | Change fatigue among clinical end users | Low | Open | Yusuf Khan
PRJ-1003 | Key SME single point of failure | Medium | Open | Fatima Al Zaabi
PRJ-1003 | Cutover rollback plan untested at scale | Low | Mitigating | Noura Al Kaabi
PRJ-1004 | Key SME single point of failure | High | Open | Aisha Al Hammadi
PRJ-1004 | Cross-program resource contention | Critical | Mitigating | Grace Okafor
PRJ-1005 | Vendor resource attrition on critical path | High | Closed | Khalid Al Marzooqi
PRJ-1005 | Budget contingency exhaustion before go-live | High | Mitigating | Khalid Al Marzooqi
PRJ-1005 | Downtime window approval risk with operations | Low | Mitigating | Noura Al Kaabi
PRJ-1010 | Third-party API instability in production | Low | Open | Ahmed Al Mansoori
PRJ-1011 | Cutover rollback plan untested at scale | Low | Open | Omar Al Shamsi
PRJ-1012 | Cross-program resource contention | High | Mitigating | Daniel Weber
PRJ-1013 | Third-party API instability in production | High | Open | Li Wei Chen
PRJ-1013 | Cutover rollback plan untested at scale | Medium | Closed | Yusuf Khan
PRJ-1015 | Third-party API instability in production | Critical | Mitigating | Daniel Weber
PRJ-1021 | Vendor resource attrition on critical path | Medium | Open | Aisha Al Hammadi
PRJ-1021 | Change fatigue among clinical end users | Low | Mitigating | Li Wei Chen
PRJ-1021 | Downtime window approval risk with operations | Low | Open | Ravi Subramanian
PRJ-1030 | Regulatory compliance deadline (DoH/NESA) slippage | Medium | Open | Mariam Al Suwaidi
PRJ-1031 | Data quality below migration threshold | High | Closed | Khalid Al Marzooqi
PRJ-1031 | Downtime window approval risk with operations | Low | Open | Priya Nair
PRJ-1031 | Cutover rollback plan untested at scale | Medium | Open | Omar Al Shamsi
PRJ-1031 | Cross-program resource contention | High | Open | Aisha Al Hammadi
PRJ-1032 | Regulatory compliance deadline (DoH/NESA) slippage | Low | Mitigating | Ravi Subramanian
PRJ-1032 | Key SME single point of failure | Low | Closed | Sara Haddad
PRJ-1033 | Downtime window approval risk with operations | Low | Open | James O'Connor
PRJ-1034 | Data quality below migration threshold | Medium | Open | Aisha Al Hammadi
PRJ-1034 | Licensing cost escalation at contract renewal | High | Open | Ravi Subramanian
PRJ-1041 | Vendor resource attrition on critical path | Low | Closed | Sara Haddad
PRJ-1042 | Vendor resource attrition on critical path | High | Open | Ravi Subramanian
PRJ-1043 | Key SME single point of failure | Low | Closed | Omar Al Shamsi
PRJ-1044 | Third-party API instability in production | Low | Open | Omar Al Shamsi
PRJ-1046 | Budget contingency exhaustion before go-live | High | Mitigating | James O'Connor
PRJ-1049 | Licensing cost escalation at contract renewal | Medium | Closed | Noura Al Kaabi
PRJ-1049 | Cross-program resource contention | Medium | Open | Saeed Al Falahi
PRJ-1050 | Integration dependency on legacy interface engine | Low | Mitigating | Ravi Subramanian
PRJ-1050 | Key SME single point of failure | Critical | Open | Mariam Al Suwaidi
PRJ-1051 | Integration dependency on legacy interface engine | Medium | Open | Daniel Weber
PRJ-1051 | Budget contingency exhaustion before go-live | High | Open | Ravi Subramanian