## Projects
PRJ ID | Name | Scope | Business Unit | Theme | Portfolio | Parent ID | Project Manager | Exec Sponsor | Partner | Status | RAG | Priority | Current Phase | Date Approved | Start | Planned End | Actual End | Total Budget | Actuals | Pct Complete | Last Modified
PRJ-3001 | OT & Building Management Security Assessment | Security assessment and remediation roadmap for building management and OT systems. | Cybersecurity | Resilience & Security |  |  | Mariam Al Suwaidi | Amna Al Ali | e& enterprise | In Progress | R | High | Execution | 2024-10-27 | 2024-12-05 | 2026-06-15 |  | 1100000 | 622000 | 60 | 2026-08-11
PRJ-3002 | Phishing Simulation & Awareness Program | Continuous phishing simulation with role-based awareness training and executive reporting. | Cybersecurity | Resilience & Security | Fortress | PRJ-1010 | James O'Connor | Mohammed Al Hashimi | CrowdStrike | In Progress | G | High | Execution | 2025-07-11 | 2025-08-12 | 2027-02-02 |  | 1250000 | 765000 | 63 | 2026-07-26
PRJ-3003 | Data Loss Prevention Rollout | Endpoint and cloud DLP policies protecting patient data across email, web and removable media. | Cybersecurity | Resilience & Security | Fortress | PRJ-1010 | James O'Connor | Eng. Salem Al Nuaimi | Microsoft | In Progress | A | Medium | Execution | 2025-07-05 | 2025-09-11 | 2027-03-11 |  | 3650000 | 2278000 | 65 | 2026-08-20
PRJ-3004 | Vulnerability Management Uplift | Risk-based vulnerability prioritization with SLA-driven remediation workflows in ITSM. | Cybersecurity | Resilience & Security |  |  | Ravi Subramanian | Dr. Hessa Al Falasi | Splunk | In Progress | G | Medium | Execution | 2025-03-10 | 2025-05-20 | 2026-10-26 |  | 1650000 | 1102000 | 73 | 2026-07-19
PRJ-3005 | Identity Governance & Administration | Joiner-mover-leaver automation, access certification and role mining for clinical systems. | Cybersecurity | Resilience & Security |  |  | Fatima Al Zaabi | Amna Al Ali | IBM Consulting | In Progress | A | Medium | Execution | 2025-06-19 | 2025-07-22 | 2027-01-11 |  | 2950000 | 2270000 | 70 | 2026-07-20
PRJ-3006 | Email Security Gateway Replacement | Cloud email security with impersonation protection replacing the legacy on-premise gateway. | Cybersecurity | Resilience & Security |  |  | Noura Al Kaabi | Mohammed Al Hashimi | Microsoft | Completed | G | Critical | Closure | 2025-02-02 | 2025-03-02 | 2026-08-28 | 2026-08-22 | 950000 | 856000 | 100 | 2026-08-21
PRJ-3007 | Red Team Exercise 2026 | Full-scope adversary simulation testing detection and response across clinical environments. | Cybersecurity | Resilience & Security |  |  | Priya Nair | Amna Al Ali | CrowdStrike | Approved | G | High | Planning | 2026-08-18 | 2026-09-20 | 2027-08-10 |  | 1700000 | 14000 | 7 | 2026-08-20
PRJ-3008 | Backup Immutability & Ransomware Vault | Immutable backup copies and an isolated recovery vault for tier-1 clinical workloads. | Cybersecurity | Resilience & Security |  |  | Li Wei Chen | Amna Al Ali | Dell Technologies | In Progress | G | High | Execution | 2025-08-15 | 2025-10-29 | 2027-03-27 |  | 7200000 | 3968000 | 58 | 2026-07-27

## Milestones
Project ID | Name | Due Date | Completed Date | Status
PRJ-3001 | Environment Provisioning Complete | 2025-05-18 | 2025-05-21 | Completed
PRJ-3001 | Data Migration Dry Run | 2025-11-06 | 2025-11-07 | Completed
PRJ-3001 | Training & Adoption Complete | 2026-04-26 |  | Overdue
PRJ-3002 | Integration Testing Complete | 2025-11-24 | 2025-11-18 | Completed
PRJ-3002 | Security & Compliance Review | 2026-03-09 | 2026-03-10 | Completed
PRJ-3002 | UAT Sign-off | 2026-06-15 | 2026-06-21 | Completed
PRJ-3002 | Training & Adoption Complete | 2026-09-12 |  | Pending
PRJ-3002 | Production Go-Live | 2027-01-04 |  | Pending
PRJ-3003 | Pilot Go-Live | 2026-02-23 | 2026-02-19 | Completed
PRJ-3003 | Production Go-Live | 2026-07-28 |  | Overdue
PRJ-3003 | Hypercare Exit | 2027-01-27 |  | In Progress
PRJ-3004 | Business Case Approved | 2025-08-06 | 2025-08-10 | Completed
PRJ-3004 | Vendor Contract Signed | 2025-11-08 | 2025-11-02 | Completed
PRJ-3004 | Environment Provisioning Complete | 2026-01-29 | 2026-01-27 | Completed
PRJ-3004 | Data Migration Dry Run | 2026-04-09 | 2026-04-14 | Completed
PRJ-3004 | UAT Sign-off | 2026-07-09 | 2026-07-09 | Completed
PRJ-3004 | Go/No-Go Readiness Review | 2026-08-21 | 2026-08-16 | Completed
PRJ-3004 | Hypercare Exit | 2026-10-06 |  | In Progress
PRJ-3005 | Vendor Contract Signed | 2025-12-23 | 2025-12-23 | Completed
PRJ-3005 | Security & Compliance Review | 2026-06-06 |  | Overdue
PRJ-3005 | Pilot Go-Live | 2026-11-14 |  | Pending
PRJ-3006 | Vendor Contract Signed | 2025-06-05 | 2025-05-31 | Completed
PRJ-3006 | Environment Provisioning Complete | 2025-09-16 | 2025-09-09 | Completed
PRJ-3006 | Integration Testing Complete | 2025-12-23 | 2025-12-24 | Completed
PRJ-3006 | Security & Compliance Review | 2026-04-08 | 2026-04-04 | Completed
PRJ-3006 | Benefits Review | 2026-07-25 | 2026-07-28 | Completed
PRJ-3007 | Environment Provisioning Complete | 2027-01-06 |  | Pending
PRJ-3007 | Data Migration Dry Run | 2027-04-12 |  | Pending
PRJ-3007 | Pilot Go-Live | 2027-07-11 |  | Pending
PRJ-3008 | Business Case Approved | 2026-02-02 | 2026-02-05 | Completed
PRJ-3008 | Environment Provisioning Complete | 2026-05-02 | 2026-05-07 | Completed
PRJ-3008 | Data Migration Dry Run | 2026-08-25 |  | Pending
PRJ-3008 | Integration Testing Complete | 2026-11-22 |  | Pending
PRJ-3008 | Security & Compliance Review | 2027-02-19 |  | In Progress

## Updates
Project ID | Date | Author | Text
PRJ-3001 | 2026-07-29 | Mariam Al Suwaidi | Recovery plan invoked: scope re-sequenced, weekly CIO checkpoint established, and e& enterprise penalties under review.
PRJ-3001 | 2026-08-11 | Mariam Al Suwaidi | Escalation: data quality remains below the migration threshold; a joint remediation cell has been stood up.
PRJ-3002 | 2026-07-02 | James O'Connor | Steering committee endorsed the revised integration plan; CrowdStrike has committed additional senior resources.
PRJ-3002 | 2026-07-14 | James O'Connor | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-3002 | 2026-07-26 | James O'Connor | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-3003 | 2026-07-02 | James O'Connor | Executive walkthrough delivered to the sponsor; James O'Connor confirmed no change to the committed scope.
PRJ-3003 | 2026-07-21 | James O'Connor | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-3003 | 2026-08-01 | James O'Connor | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-3003 | 2026-08-20 | James O'Connor | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-3004 | 2026-07-06 | Ravi Subramanian | Steering committee endorsed the revised integration plan; Splunk has committed additional senior resources.
PRJ-3004 | 2026-07-19 | Ravi Subramanian | Executive walkthrough delivered to the sponsor; Ravi Subramanian confirmed no change to the committed scope.
PRJ-3005 | 2026-07-10 | Fatima Al Zaabi | Budget review completed with Finance; forecast remains within the approved envelope.
PRJ-3005 | 2026-07-20 | Fatima Al Zaabi | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-3006 | 2026-07-08 | Noura Al Kaabi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-3006 | 2026-07-27 | Noura Al Kaabi | Executive walkthrough delivered to the sponsor; Noura Al Kaabi confirmed no change to the committed scope.
PRJ-3006 | 2026-08-11 | Noura Al Kaabi | UAT defect burn-down is ahead of plan; clinical champions engaged for adoption readiness.
PRJ-3006 | 2026-08-21 | Noura Al Kaabi | Project formally closed. Hypercare exited with zero Sev-1 incidents; benefits realization transferred to the service owner.
PRJ-3007 | 2026-08-08 | Priya Nair | Sprint review complete; delivery tracking at 7% with the critical path stable.
PRJ-3007 | 2026-08-20 | Priya Nair | Funding released by the Digital Investment Committee; resource onboarding and environment requests initiated.
PRJ-3008 | 2026-07-04 | Li Wei Chen | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-3008 | 2026-07-17 | Li Wei Chen | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-3008 | 2026-07-27 | Li Wei Chen | Steering committee endorsed the revised integration plan; Dell Technologies has committed additional senior resources.

## Risks
Project ID | Title | Severity | Status | Owner
PRJ-3001 | Licensing cost escalation at contract renewal | High | Open | Saeed Al Falahi
PRJ-3001 | Cutover rollback plan untested at scale | Medium | Open | Saeed Al Falahi
PRJ-3002 | Downtime window approval risk with operations | High | Closed | James O'Connor
PRJ-3002 | Cutover rollback plan untested at scale | High | Open | Yusuf Khan
PRJ-3003 | Downtime window approval risk with operations | Medium | Closed | Priya Nair
PRJ-3004 | Data quality below migration threshold | Medium | Mitigating | Omar Al Shamsi
PRJ-3004 | Key SME single point of failure | Low | Open | Sara Haddad
PRJ-3005 | Data quality below migration threshold | Medium | Open | Fatima Al Zaabi
PRJ-3005 | Regulatory compliance deadline (DoH/NESA) slippage | High | Open | Ahmed Al Mansoori
PRJ-3005 | Cross-program resource contention | Critical | Open | Elena Petrova
PRJ-3007 | Budget contingency exhaustion before go-live | High | Closed | Khalid Al Marzooqi
PRJ-3007 | Key SME single point of failure | Medium | Open | Fatima Al Zaabi
PRJ-3008 | Downtime window approval risk with operations | Low | Mitigating | Grace Okafor