## Projects
ID | Title | Summary | Dept | Strategic Pillar | Programme | Parent Project | PM | Executive Sponsor | Supplier | Project Status | RAG Status | Criticality | Project Phase | Approved On | Kickoff Date | Target Completion | Completion Date | Approved Budget | Spent To Date | Progress | Updated On
PRJ-2001 | Ambulatory EMR Extension | Extending the OneCare EMR build to ambulatory clinics and specialty outpatient centers. | Digital Health | Digital Transformation | OneCare EMR | PRJ-1001 | Omar Al Shamsi | Eng. Salem Al Nuaimi | Epic Systems | In Progress | At Risk | High | Monitoring | 2025-03-16 | 2025-06-01 | 2026-10-15 |  | 7400000 | 6441000 | 0.9 | 2026-07-29
PRJ-2002 | Patient Portal Lab Results Release | Automated, clinically governed release of laboratory results to the patient portal. | Digital Health | Patient-Centric Care | OneCare EMR | PRJ-1001 | James O'Connor | Eng. Salem Al Nuaimi | Epic Systems | In Progress | On Track | High | Monitoring | 2025-08-17 | 2025-11-04 | 2026-11-25 |  | 1650000 | 1186000 | 0.78 | 2026-08-05
PRJ-2003 | Nursing e-Observations Rollout | Digital vital-signs capture with early-warning scoring at the bedside across wards. | Digital Health | Patient-Centric Care |  |  | Khalid Al Marzooqi | Saif Al Dhaheri | Philips | In Progress | On Track | Low | Monitoring | 2024-10-14 | 2024-12-28 | 2026-10-25 |  | 6150000 | 4311000 | 0.77 | 2026-07-21
PRJ-2004 | Smart Bed Integration Pilot | Connected smart beds streaming pressure and exit alarms into the nursing dashboard. | Digital Health | Intelligent Enterprise |  |  | Noura Al Kaabi | Mohammed Al Hashimi | Philips | In Progress | At Risk | High | Execution | 2025-11-05 | 2026-01-19 | 2026-12-14 |  | 1450000 | 1017000 | 0.67 | 2026-07-15
PRJ-2005 | Voice Dictation for Clinicians | Ambient speech-to-text clinical documentation embedded in the EMR for 1,200 physicians. | Digital Health | Operational Excellence |  |  | Ahmed Al Mansoori | Dr. Vandana Sharma | Microsoft | Completed | On Track | Medium | Closure | 2025-08-12 | 2025-10-13 | 2026-08-10 | 2026-08-18 | 650000 | 629000 | 1 | 2026-08-22
PRJ-2006 | Clinical Photography App | Secure wound and dermatology photography flowing directly into the patient record. | Digital Health | Patient-Centric Care |  |  | Sara Haddad | Dr. Hessa Al Falasi | Cisco | In Progress | On Track | High | Execution | 2026-08-10 | 2026-08-17 | 2027-02-26 |  | 1700000 | 272000 | 0.15 | 2026-07-26
PRJ-2007 | Imaging AI Triage | AI triage of chest X-rays and CT heads prioritizing critical findings for radiologists. | Data & AI | Intelligent Enterprise | Insight | PRJ-1020 | Li Wei Chen | Dr. Richard Hughes | GE HealthCare | In Progress | On Track | Medium | Execution | 2024-12-09 | 2025-02-13 | 2027-02-18 |  | 2500000 | 1990000 | 0.74 | 2026-07-18
PRJ-2008 | Digital Consent Workflow | Paperless surgical and procedural consent with multilingual forms and e-signature. | Digital Health | Patient-Centric Care |  |  | Li Wei Chen | Saif Al Dhaheri | ServiceNow | Approved | On Track | High | Planning | 2026-08-17 | 2026-09-02 | 2027-11-17 |  | 1450000 | 28000 | 0.08 | 2026-08-23
PRJ-2009 | Bedside Tablet Experience | Bedside tablets for meal ordering, education content and environment controls. | Patient Experience | Patient-Centric Care |  |  | Ravi Subramanian | Dr. Richard Hughes | Splunk | Proposed | On Track | High | Initiation |  | 2027-01-11 | 2027-11-30 |  | 950000 | 0 | 0.02 | 2026-07-24
PRJ-2010 | e-Referrals Interoperability Gateway | National e-referral exchange gateway conforming to federal interoperability standards. | Digital Health | Digital Transformation |  |  | James O'Connor | Eng. Salem Al Nuaimi | Injazat | In Progress | Off Track | High | Execution | 2025-04-27 | 2025-07-01 | 2026-08-05 |  | 6200000 | 3175000 | 0.55 | 2026-08-20

## Milestones
Project ID | Name | Due Date | Completed Date | Status
PRJ-2001 | Business Case Approved | 2025-08-10 | 2025-08-16 | Completed
PRJ-2001 | Vendor Contract Signed | 2025-10-29 | 2025-10-27 | Completed
PRJ-2001 | Solution Design Sign-off | 2026-01-24 | 2026-01-26 | Completed
PRJ-2001 | Integration Testing Complete | 2026-04-13 |  | Overdue
PRJ-2001 | Training & Adoption Complete | 2026-07-06 |  | Overdue
PRJ-2001 | Production Go-Live | 2026-09-12 |  | Pending
PRJ-2002 | Vendor Contract Signed | 2026-01-05 | 2026-01-04 | Completed
PRJ-2002 | Data Migration Dry Run | 2026-03-27 | 2026-03-26 | Completed
PRJ-2002 | Training & Adoption Complete | 2026-06-05 | 2026-06-13 | Completed
PRJ-2002 | Production Go-Live | 2026-08-16 | 2026-08-17 | Completed
PRJ-2002 | Hypercare Exit | 2026-10-25 |  | Pending
PRJ-2003 | Business Case Approved | 2025-04-10 | 2025-04-12 | Completed
PRJ-2003 | Vendor Contract Signed | 2025-08-04 | 2025-08-05 | Completed
PRJ-2003 | Solution Design Sign-off | 2025-11-18 | 2025-11-26 | Completed
PRJ-2003 | Data Migration Dry Run | 2026-03-04 | 2026-03-06 | Completed
PRJ-2003 | Integration Testing Complete | 2026-06-06 | 2026-05-31 | Completed
PRJ-2003 | Go/No-Go Readiness Review | 2026-08-23 |  | In Progress
PRJ-2003 | Benefits Review | 2026-09-27 |  | Pending
PRJ-2004 | Business Case Approved | 2026-03-06 | 2026-03-03 | Completed
PRJ-2004 | Solution Design Sign-off | 2026-05-01 |  | Overdue
PRJ-2004 | Environment Provisioning Complete | 2026-06-15 | 2026-06-13 | Completed
PRJ-2004 | Integration Testing Complete | 2026-08-20 | 2026-08-17 | Completed
PRJ-2004 | UAT Sign-off | 2026-10-01 |  | Pending
PRJ-2004 | Benefits Review | 2026-11-18 |  | Pending
PRJ-2005 | Business Case Approved | 2025-12-03 | 2025-11-30 | Completed
PRJ-2005 | Environment Provisioning Complete | 2026-01-31 | 2026-01-24 | Completed
PRJ-2005 | Data Migration Dry Run | 2026-04-10 | 2026-04-14 | Completed
PRJ-2005 | Pilot Go-Live | 2026-05-25 | 2026-05-19 | Completed
PRJ-2005 | Benefits Review | 2026-08-05 | 2026-08-04 | Completed
PRJ-2006 | Data Migration Dry Run | 2026-10-04 |  | Pending
PRJ-2006 | Integration Testing Complete | 2026-11-09 |  | In Progress
PRJ-2006 | Security & Compliance Review | 2026-12-28 |  | Pending
PRJ-2006 | Production Go-Live | 2027-02-11 |  | Pending
PRJ-2007 | Solution Design Sign-off | 2025-06-11 | 2025-06-07 | Completed
PRJ-2007 | Environment Provisioning Complete | 2025-10-14 | 2025-10-18 | Completed
PRJ-2007 | Security & Compliance Review | 2026-02-03 | 2026-02-10 | Completed
PRJ-2007 | Training & Adoption Complete | 2026-05-15 | 2026-05-16 | Completed
PRJ-2007 | Production Go-Live | 2026-09-29 |  | Pending
PRJ-2007 | Benefits Review | 2027-01-23 |  | In Progress
PRJ-2008 | Business Case Approved | 2026-11-07 |  | Pending
PRJ-2008 | Vendor Contract Signed | 2027-01-10 |  | Pending
PRJ-2008 | Environment Provisioning Complete | 2027-03-23 |  | Pending
PRJ-2008 | Integration Testing Complete | 2027-06-03 |  | Pending
PRJ-2008 | Production Go-Live | 2027-08-08 |  | Pending
PRJ-2008 | Benefits Review | 2027-11-04 |  | Pending
PRJ-2009 | Vendor Contract Signed | 2027-03-10 |  | Pending
PRJ-2009 | Environment Provisioning Complete | 2027-04-17 |  | Pending
PRJ-2009 | Data Migration Dry Run | 2027-06-16 |  | Pending
PRJ-2009 | Pilot Go-Live | 2027-07-28 |  | Pending
PRJ-2009 | Training & Adoption Complete | 2027-09-30 |  | Pending
PRJ-2009 | Hypercare Exit | 2027-11-04 |  | Pending
PRJ-2010 | Vendor Contract Signed | 2025-10-12 | 2025-10-09 | Completed
PRJ-2010 | Environment Provisioning Complete | 2026-01-05 | 2026-01-12 | Completed
PRJ-2010 | Security & Compliance Review | 2026-03-27 |  | Overdue
PRJ-2010 | UAT Sign-off | 2026-06-30 |  | Overdue

## Updates
Project ID | Date | Author | Text
PRJ-2001 | 2026-07-07 | Omar Al Shamsi | Sprint review complete; delivery tracking at 90% with the critical path stable.
PRJ-2001 | 2026-07-17 | Omar Al Shamsi | Steering committee endorsed the revised integration plan; Epic Systems has committed additional senior resources.
PRJ-2001 | 2026-07-29 | Omar Al Shamsi | Steering committee endorsed the revised integration plan; Epic Systems has committed additional senior resources.
PRJ-2002 | 2026-07-03 | James O'Connor | Steering committee endorsed the revised integration plan; Epic Systems has committed additional senior resources.
PRJ-2002 | 2026-07-22 | James O'Connor | Executive walkthrough delivered to the sponsor; James O'Connor confirmed no change to the committed scope.
PRJ-2002 | 2026-08-05 | James O'Connor | Steering committee endorsed the revised integration plan; Epic Systems has committed additional senior resources.
PRJ-2003 | 2026-07-02 | Khalid Al Marzooqi | Sprint review complete; delivery tracking at 77% with the critical path stable.
PRJ-2003 | 2026-07-21 | Khalid Al Marzooqi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-2004 | 2026-06-26 | Noura Al Kaabi | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-2004 | 2026-07-15 | Noura Al Kaabi | Executive walkthrough delivered to the sponsor; Noura Al Kaabi confirmed no change to the committed scope.
PRJ-2005 | 2026-08-04 | Ahmed Al Mansoori | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-2005 | 2026-08-22 | Ahmed Al Mansoori | Closure report approved by the steering committee; residual actions handed to operations with owners and dates.
PRJ-2006 | 2026-07-03 | Sara Haddad | Steering committee endorsed the revised integration plan; Cisco has committed additional senior resources.
PRJ-2006 | 2026-07-18 | Sara Haddad | Executive walkthrough delivered to the sponsor; Sara Haddad confirmed no change to the committed scope.
PRJ-2006 | 2026-07-26 | Sara Haddad | Interface build with the enterprise service bus passed end-to-end validation in staging.
PRJ-2007 | 2026-06-30 | Li Wei Chen | Testing exit criteria agreed with Quality & Patient Safety; entry into performance testing next week.
PRJ-2007 | 2026-07-18 | Li Wei Chen | Executive walkthrough delivered to the sponsor; Li Wei Chen confirmed no change to the committed scope.
PRJ-2008 | 2026-07-19 | Li Wei Chen | Steering committee endorsed the revised integration plan; ServiceNow has committed additional senior resources.
PRJ-2008 | 2026-08-08 | Li Wei Chen | Sprint review complete; delivery tracking at 8% with the critical path stable.
PRJ-2008 | 2026-08-23 | Li Wei Chen | Funding released by the Digital Investment Committee; resource onboarding and environment requests initiated.
PRJ-2009 | 2026-07-12 | Ravi Subramanian | Sprint review complete; delivery tracking at 2% with the critical path stable.
PRJ-2009 | 2026-07-24 | Ravi Subramanian | Discovery workshops completed with clinical stakeholders; benefits model circulated for sponsor endorsement.
PRJ-2010 | 2026-07-12 | James O'Connor | Schedule re-baseline submitted to the portfolio board; dependency on the legacy interface engine confirmed as root cause.
PRJ-2010 | 2026-07-23 | James O'Connor | Steering committee endorsed the revised integration plan; Injazat has committed additional senior resources.
PRJ-2010 | 2026-08-03 | James O'Connor | Schedule re-baseline submitted to the portfolio board; dependency on the legacy interface engine confirmed as root cause.
PRJ-2010 | 2026-08-20 | James O'Connor | Schedule re-baseline submitted to the portfolio board; dependency on the legacy interface engine confirmed as root cause.

## Risks
Project ID | Title | Severity | Status | Owner
PRJ-2001 | Licensing cost escalation at contract renewal | Critical | Closed | Grace Okafor
PRJ-2002 | Regulatory compliance deadline (DoH/NESA) slippage | Medium | Open | Sara Haddad
PRJ-2002 | Cutover rollback plan untested at scale | High | Open | Ravi Subramanian
PRJ-2004 | Integration dependency on legacy interface engine | Medium | Closed | Li Wei Chen
PRJ-2004 | Regulatory compliance deadline (DoH/NESA) slippage | Low | Mitigating | Omar Al Shamsi
PRJ-2006 | Downtime window approval risk with operations | High | Mitigating | Saeed Al Falahi
PRJ-2007 | Vendor resource attrition on critical path | Low | Mitigating | Yusuf Khan
PRJ-2007 | Licensing cost escalation at contract renewal | Low | Mitigating | Grace Okafor
PRJ-2008 | Downtime window approval risk with operations | Low | Open | Mariam Al Suwaidi
PRJ-2008 | Cutover rollback plan untested at scale | Low | Closed | Fatima Al Zaabi
PRJ-2009 | Regulatory compliance deadline (DoH/NESA) slippage | Low | Open | Omar Al Shamsi
PRJ-2009 | Cutover rollback plan untested at scale | Low | Open | Omar Al Shamsi
PRJ-2010 | Vendor resource attrition on critical path | Critical | Mitigating | Grace Okafor
PRJ-2010 | Regulatory compliance deadline (DoH/NESA) slippage | High | Open | Omar Al Shamsi